## Sheet1
project_id | project_name | rating_date | optic_name | rating | justification
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | firmness_of_opportunity | Red | DAF / GIP or 'one pager' not yet prepared. Approvals not expected for >3 months. Start date of IT effort unknown
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | business_case | Amber | There is mention that 'Pilot customer may not be able to participate as internal reorg is taking their focus, still planned to show by end of Aug the demo. Alternative customers identified for pilot if required.' This suggests ongoing work on business case issues as the original benefits case related to the pilot customer needs revisiting and alternative strategies are being considered.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | business_requirements | Red | Inadequately defined requirements. The project status report does not mention any clear definition or documentation of requirements for impacted portfolios. The focus is on technical and scheduling challenges.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | solution​ | Amber | There is mention in multiple sections that additional work and final approvals are still needed. Specifically, the 'Challenges & RTG' section notes 'Market Data Agreements may not be agreed with ICE exchange prior to go-live' and 'Legal drafting a letter to reinstate ask', which indicates that the solutions have not been fully understood or agreed upon. The unresolved legal and market data agreement suggests that the solution is not yet fully defined, requiring additional work.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | commercialops_functions_support​ | Amber | The executive summary mentions that 'Global Support Model: Internal model being discussed with the IT Management,' indicating that there may be ongoing discussions on support needs and possibly additional staff requirements. No evidence suggests a current lack of required skills, but the need for additional or prioritization suggests an Amber rating.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | ts_process_team_within_comm_ops_bia_org​ | Green | The project status report indicates that 'Concerns & RTG: None' and 'Things that went well', implying that the existing staff can deliver the work without additional resources or need for prioritization. This aligns with the criteria for a Green rating, indicating that the existing staff are capable of delivering the necessary work.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | owning_portfolio_it_resource_capacity​ | Green | The project status report indicates successful completion of several activities such as 'Sept Quarterly Release: C Migration: Completed' and 'UAT/ITC: Completed'. Additionally, sections titled 'EXECUTIVE SUMMARY' and 'GENERAL COMMENTS' mention that there are 'Concerns & RTG: None' and 'Things that went well – UAT/ITC: Completed', which indicates that existing staff can deliver the work without the need for additional resources or prioritization. This aligns with the criteria for a Green rating.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | ongoing_supportability_of_solution​​ | Red | The project status report lacks explicit mention of the solution fitting within an existing support model or contract. It discusses ongoing deliverables and technical progress but fails to detail whether a current support model exists or if amendments or new support structures are needed. Additionally, the mention of continuous analysis without clarity on support models or contracts suggests an assumption of a support structure that doesn’t clearly align with existing models.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | effective_governance​ | Red | The project status report does not mention any governance model being defined, agreed, or even drafted. It lacks any details regarding a governance model addressing the project scope and risk, or a clear decision owner being identified. Based on the criteria, the appropriate rating is Red, as the governance model has not yet been drafted, according to the information provided.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | partnership_and_collaboration | Green | The project status report shows continuous completion of deliverables, such as 'ITC/UAT: Completed' and 'Scoped and Design Closure: Completed'. The repeated collaborative success between Business and IT teams indicates a history of effective cooperation. Therefore, it aligns with the criteria where 'Business and IT teams have delivered projects together in the past and have a strong working relationship'.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | business_case | Red | Don't have the data to provide.'
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | business_requirements | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | solution​ | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | estimate_budget_accuracy​ | Amber | Cost (Amber): LE & budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | commercialops_functions_support​ | Green | The project has successfully gone live with Carbon IQ and Kendo to SDS Migration was completed on 18th July with no indication of additional staffing needs or skill shortages. There is no mention of lack of skills or capabilities, indicating existing staff can deliver all necessary work.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | ts_and_broader_rds_it_resource_Capacity | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | ts_process_team_within_comm_ops_bia_org​ | Green | The project status report does not indicate any need for additional staff or prioritization calls, nor does it mention any lack of resources or skills. Therefore, it is implied that existing staff can deliver the work associated with this project.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | owning_portfolio_it_resource_capacity​ | Green | The project status report does not indicate any need for additional staff or prioritization calls, nor does it mention any lack of resources or skills. Therefore, it is implied that existing staff can deliver the work associated with this project.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | ongoing_supportability_of_solution​​ | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | effective_governance​ | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | partnership_and_collaboration | Red | Don't have the data to provide.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | estimate_budget_accuracy​ | Red | There is no direct evidence in the project status report indicating a capacity or scope-based estimate with a specific confidence level. The report discusses schedule and externalization challenges, such as 'Schedule (Red): Externalisation: Market Data Agreements may not be agreed with ICE exchange prior to go-live' and 'Legal drafting a letter to reinstate ask,' which implies a high level of uncertainty, consistent with a planning number based on little science with +/- 50% level of confidence.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | ts_and_broader_rds_it_resource_Capacity | Amber | The executive summary states: 'Global Support Model: Internal model being discussed with the IT Management. Final step is to go to Owen O'Connell in Sept for approval.' This suggests that discussions have taken place, but no firm commitments have been made. The current status aligns with the criteria for Amber: 'Request made, no firm commitments made.​'
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | ts_process_team_within_comm_ops_bia_org​ | Green | There is no mention in the project status report that additional staff or specific prioritisation calls are needed. The achievements and progress sections indicate ongoing developments and deployments without direct evidence of resource shortages or skill gaps, thus satisfying the criteria that 'Existing staff can deliver the work.'
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | owning_portfolio_it_resource_capacity​ | Green | The project status report does not explicitly mention any lack of resources or skill gaps that would hinder the current progress. All scheduled activities and achievements describe successful deployments and protected timelines, implying that the current staffing suffices to deliver the work, satisfying the criteria for a Green rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | ongoing_supportability_of_solution​​ | Amber | The project status report states: 'Final step is to go to Owen O'Connell in Sept for approval.' Additionally, 'Global Support Model: Internal model being discussed with the IT Management,' indicates that amendments to an existing support model / contract or new support requirements are potentially being considered and are in scope for delivery, suggesting an Amber rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | effective_governance​ | Red | There is no direct evidence in the project status report of a governance model being defined, agreed across stakeholders, or even drafted. The absence of mention regarding a governance model indicates that it has not yet been drafted.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | partnership_and_collaboration | Red | The project status report does not mention any prior collaborations or established relationships between the Business and IT teams. Furthermore, there is no evidence of a strong working relationship or past project deliveries together, and there are no specifics on team building or relationship improvement activities required, leading to the default assumption that the relationship is not well-established.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | firmness_of_opportunity | Red | The project status report does not mention any 'DAF / GIP or one pager' being prepared or approvals being obtained. Additionally, a start date for an IT effort is not noted, nor is one mentioned as tentative. The available information discusses progress and achievements, but does not provide the necessary details required for a Green or Amber rating under the 'firmness_of_opportunity' criteria. Therefore, based on the criteria and the information available, the rating is Red.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | business_case | Amber | The available information discusses completed activities and planned activities, but it does not explicitly mention defined L1 and/or L2 benefits with agreed benefit owners. It mentions that 'Business Impact Assessment for Sept Quarterly Release Completed' and 'Discussion on re-assessment of BIA/LRA has been initiated' which suggests that benefits case is in progress or needs revisiting. There is not enough information to confirm if L1 and/or L2 benefits are defined, thus it rates as Amber.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | business_requirements | Green | The project status report indicates successes such as 'Sept Quarterly Release Deliverables...Scope and Design/ALM UAT Setup: Completed' and 'November Quarterly Release Scope & Design Closure: Completed'. Additionally, there is continual progress with 'Apollo E2E Re-Risk Assessment: IAQ-completed'. These completions suggest that requirements for impacted portfolios are clearly defined and documented, meeting the criteria for a Green rating.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | solution​ | Amber | While there is significant progress in project deliverables such as 'Nov Quarterly Release: Scope & Design Closure in Progress' and 'ITC/UAT: Completed' for the Sept quarterly release, the report indicates further scope and design closure for future releases being in progress, which implies that some additional time or work is needed to fully define the solution. This matches the criteria for an Amber rating.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | estimate_budget_accuracy​ | Red | The project status report does not provide any specific data about budget estimates or the confidence level in these estimates. There is no mention of capacity or scope-based estimates, nor any percentage levels of confidence associated with these estimates. The available information discusses progress and achievements but lacks details pertaining to budget estimations. Therefore, based on the criteria of having either a +/- 20%, +/- 30%, or +/- 50% level of confidence in the budget estimates, the only fitting rating is Red, indicating the planning number is based on little science with +/- 50% level of confidence.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | commercialops_functions_support​ | Green | The project status report does not indicate any concerns regarding staffing needs. The sections titled 'EXECUTIVE SUMMARY' and 'GENERAL COMMENTS' both mention that there are no current concerns or risks ('Concerns & RTG: None' and 'Things that went well – UAT/ITC: Completed'), implying that the existing staff can handle the necessary workload effectively. This aligns with the criteria for a Green rating, indicating that the current team can deliver all necessary work.
PRJ4880631 | 2025 - Apollo Enhancements | 2025-09-20 | ts_and_broader_rds_it_resource_Capacity | Amber | The project status report does not provide specific evidence that resource discussions have taken place and commitments obtained. It also does not mention requests being made with no resources available or lacking required skills. However, there is a general sense of progress without specific mention of resource commitments, fitting the Amber rating: 'Request made, no firm commitments made'.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | firmness_of_opportunity | Red | The direct quote from the text that proves your rating. If no direct evidence exists, the say don't have the data to provide.'
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | firmness_of_opportunity | Red | DAF / GIP or 'one pager' not yet prepared. Approvals not expected for >3 months. Start date of IT effort unknown.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | business_case | Green | The project status report includes benefits described as 'The 'HVO B7' tool is projected to generate approximately $3 million per annum in tax rebates for Shell, with the value poised to grow as sales of HVO B7 continue to increase.' Additionally, '31 m$ / year level 1/level 2 Europe benefits were confirmed, down from 55 m$/year.' This indicates the presence of L1 and/or L2 benefits as defined by the project with agreed benefit ownership.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | business_requirements | Green | The project closure activities are in progress with successful completion of Hypercare and business sign-off, reflecting well-documented requirements for impacted portfolios. The consistent and ongoing completion of tasks and achievements, such as finalized technical documentation and agreed deployment plans, supports readiness to mobilize.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | solution​ | Green | Progress & Success: Hypercare successfully completed and ATO signed-off as per plan. Project team dispersed. Closure activities are in progress. The 'HVO B7' tool is projected to generate approximately $3 million per annum in tax rebates for Shell, with the value poised to grow as sales of HVO B7 continue to increase. Challenges & RTGs: None
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | estimate_budget_accuracy​ | Red | Cost (RED): $750k budget approved through to the end of July has been spent. RTG: Sandeep to request bridge funding of $250k cover until end of Sep'25 and GIP approval.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | commercialops_functions_support​ | Green | Project team already provided hand over to the support team regarding the changes they need to make. This implies that existing staff can deliver all necessary work as the project is in its closing phase and no specific skill gaps or resource needs are mentioned.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | ts_and_broader_rds_it_resource_Capacity | Green | Worked with CC team and managed to retain the primary data engineer to continue work on the project, hence the associated risk is mitigated now and Resourcing status moved back to Green.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | ts_process_team_within_comm_ops_bia_org​ | Green | Project team already provided hand over to the support team regarding the changes they need to make. This implies that existing staff can deliver all necessary work as the project is in its closing phase and no specific skill gaps or resource needs are mentioned.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | owning_portfolio_it_resource_capacity​ | Green | Project team already provided hand over to the support team regarding the changes they need to make. This implies that existing staff can deliver all necessary work as the project is in its closing phase and no specific resource shortages or skill gaps are mentioned.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | ongoing_supportability_of_solution​​ | Green | Project team already provided hand over to the support team regarding the changes they need to make. Additionally, Hypercare was successfully completed with sign-off from Business, which indicates that the solution fits within an existing support model or contract, fulfilling the criteria for Green.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | effective_governance​ | Red | The project status report does not contain any mention of a governance model being defined, drafted, or agreed upon, nor a clear decision owner identified. Therefore, the rating is Red because 'Governance model not yet drafted'.
PRJ4897790 | 2025 Planning and Scheduling IDT Work | 2025-09-23 | partnership_and_collaboration | Green | Hypercare successfully completed and received sign-off from Business. Additionally, there is evidence of coordinated efforts between various teams, such as the AMDP team working with T&S support to make appropriate changes, and technical documentation being shared with the support team. These imply a strong working relationship between business and IT teams, meeting the criteria for Green.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | firmness_of_opportunity | Amber | The project status report mentions 'IDT & Business cost estimates have been completed for the GIP. ... GIP is in draft, IT costs and plans developed, business still refining the actual value case, one month behind plan. RTG: Plan to complete and sign-off GIP by end of Aug.' This indicates that the GIP is in progress and approvals are expected within a short-term period, matching the criteria for an Amber rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | business_case | Amber | The project status report indicates that there is progress on the benefits case but no explicit confirmation of defined L1 and/or L2 benefits with agreed benefit owners. It states 'GIP is in draft, IT costs and plans developed, business still refining the actual value case, one month behind plan. RTG: Plan to complete and sign-off GIP by end of Aug, aligned with key business stakeholders.' This suggests the benefits case is in progress or needs revisiting, aligning with the Amber criteria.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | business_requirements | Red | The project status report does not directly address the requirements related to business requirements being clearly defined and documented. The report mainly discusses technical and scheduling aspects and lacks any mention of documented business requirements or readiness for mobilization. Therefore, based on the absence of evidence aligning with the criteria for Green or even Amber, the rating is Red because there is inadequate direct evidence of defined requirements.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | solution​ | Amber | The text mentions 'Technical & functional readiness on track for Sept' and challenges like 'Market Data Agreements may not be agreed with ICE exchange prior to go-live. Need agreement by end of Aug if we are to stick with the go-live end of Sept.' Additionally, the 'Pilot customer may not be able to participate as internal reorg is taking their focus,' which implies that more time/work is needed to define the solution completely. This aligns with the Amber criteria: Additional time/work needed to define solution.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | estimate_budget_accuracy​ | Red | The text includes a statement 'Cost (RED): $750k budget approved through to the end of July has been spent. RTG: Sandeep to request bridge funding of $250k cover until end of Sep&#39;25 and GIP approval.' This indicates that the budgeting is based on less certainty, aligning with the criteria for a Red rating where planning is based on little science with +/- 50% level of confidence.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | commercialops_functions_support​ | Green | The project status report does not indicate any issues with staffing or required capabilities. There is no mention of needing additional staff or lacking required skills. The existing operations such as Henry Hub onboarding and deployment of DSX updates, as well as the planned releases and disaster recovery exercises, suggest that existing staff are handling the necessary work competently. This aligns with the criteria for a Green rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | ts_and_broader_rds_it_resource_Capacity | Red | The project status report does not mention any specific resource discussions or commitments made. There is no evidence of resource availability or skill capabilities addressed in the text. Hence, the rating is Red as per the criteria: Request made and no resources available and/or lack of required skills/capabilities.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | ts_process_team_within_comm_ops_bia_org​ | Green | The project status report does not indicate any issues with staffing or a lack of required skills. There is no mention of a need for additional staff or prioritization calls related to staffing. The ongoing work such as the successful deployment of DSX updates and planned disaster recovery exercises suggests that existing staff can deliver the work. This aligns with the criteria for a Green rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | owning_portfolio_it_resource_capacity​ | Green | The project status report does not indicate any issues with staffing or a shortage of required capabilities. There are no mentions of needing additional staff or prioritization calls for resource allocation. Existing operations, including releases and deployment activities, along with the planned disaster recovery exercises, imply that the existing staff is capable of delivering the work. This aligns with the criteria for a Green rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | ongoing_supportability_of_solution​​ | Red | The project status report mentions 'Global Support Model: Internal model being discussed with the IT Management. Final step is to go to Owen O'Connell in Sept for approval.' This indicates that the support model is still under discussion and requires further approval, which aligns with the criteria for a Red rating where the support model is unclear or still being established.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | effective_governance​ | Red | The project status report does not provide any specific mention of a governance model being defined, drafted, or agreed upon with IT and Business stakeholders. There is no evidence of clear decision ownership or governance addressing project scope and risk. Hence, based on the criteria, the rating is Red: Governance model not yet drafted.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-23 | partnership_and_collaboration | Green | The project status report includes evidence of successful past collaboration between business and IT teams as indicated by achievements such as 'Successfully established and enabled AES-to-TT VPN connectivity in Production' and 'DSX v115, AES v5.8 & DSP v2.69 were successfully deployed to Production, marking a key milestone in our strategic roadmap.' These milestones suggest that the business and IT teams have delivered projects together successfully in the past and have a strong working relationship.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | firmness_of_opportunity | Amber | DAF / GIP or 'one pager' not yet prepared. Approvals not expected for >3 months. Start date of IT effort unknown. There is no direct mention of DAF/GIP being prepared or internal approvals being secured, nor a known start date for IT effort in the provided project status report. Based on the criteria, the conditions match the RED rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | business_case | Amber | The project status report does not provide evidence of L1 and/or L2 benefits with defined benefit owners. There are mentions of milestones and achievements, but no direct information on a defined benefits case or benefit owners. Thus, according to the criteria, it falls under 'No Benefits case developed / existing benefits no longer valid'.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | business_requirements | Red | The project status report lacks definite evidence of clearly defined and documented requirements in a Charter or similar document. Instead, the report highlights challenges such as market data agreements with ICE exchange not being confirmed, as well as resource hiring delays, indicating that the requirements are inadequately defined. Therefore, it matches the criteria for a RED rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | solution​ | Amber | While there are multiple developments and planning in place, such as the Henry Hub onboarding, scheduled feature releases, and disaster recovery exercises, there are still ongoing challenges like unresolved market data agreements with ICE and resource issues. This indicates that additional time/work is needed to fully define and solidify the solution.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | estimate_budget_accuracy​ | Green | Comments on Cost: Costs are in line with budgets. This statement indicates that the project estimates are holding within a reasonable margin of the budget, suggesting a confidence level within +/- 20%, which aligns with the criteria for a GREEN rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | commercialops_functions_support​ | Red | Additional BA & Dev need to be hired into Houston and resume quality remains unsatisfactory, this will extend times to build the team. Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. Endur resources have not arrived as anticipated as they have been prioritised by the cc onto other projects. These points highlight a lack of required skills and capabilities, matching the RED rating criteria.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | ts_and_broader_rds_it_resource_Capacity | Red | Additional BA & Dev need to be hired into Houston and resume quality remains unsatisfactory, this will extend times to build the team. Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. Endur resources have not arrived as anticipated as they have been prioritised by the cc onto other projects. These points highlight a lack of required skills and capabilities, matching the RED rating criteria.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | ts_process_team_within_comm_ops_bia_org​ | Amber | Comments on Resources: Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. This shows that additional staff is needed, which matches the criteria for an AMBER rating where additional staff needed and/or a prioritisation call is needed.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | owning_portfolio_it_resource_capacity​ | Amber | Comments on Resources: Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. This indicates that additional staff is needed, which matches the criteria for an AMBER rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | ongoing_supportability_of_solution​​ | Red | Global Support Model: Internal model being discussed with the IT Management. Final step is to go to Owen O'Connell in Sept for approval. This indicates that the support model is still under discussion and has not yet been approved, meeting the criteria where the support model is unclear.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | effective_governance​ | Red | The project status report does not provide any specific information that a governance model has been drafted, agreed upon, or defined across IT and Business stakeholders. Additionally, there is no mention of a decision owner being identified, which fulfills the RED rating criteria since it indicates 'Governance model not yet drafted'.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | partnership_and_collaboration | Red | Business and IT teams do not have experience working together OR have experience but relationship is challenged. The project status report indicates significant challenges, such as 'Morgan Stanley (Euronext) connectivity not working and response from the bank have been lacklustre,' and issues with hiring additional BA & Dev in Houston, which impacts team collaboration efforts. This fulfills the criteria for RED as it indicates a challenged relationship.