## Sheet1
project_id | project_name | rating_date | optic_name | rating | justification
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | firmness_of_opportunity | Red | The direct quote from the text that proves your rating. If no direct evidence exists, the say don't have the data to provide.'
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | business_case | Red | Don't have the data to provide.'
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | business_requirements | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | solution​ | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | estimate_budget_accuracy​ | Amber | Cost (Amber): LE & budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | commercialops_functions_support​ | Green | The project has successfully gone live with Carbon IQ and Kendo to SDS Migration was completed on 18th July with no indication of additional staffing needs or skill shortages. There is no mention of lack of skills or capabilities, indicating existing staff can deliver all necessary work.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | ts_and_broader_rds_it_resource_Capacity | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | ts_process_team_within_comm_ops_bia_org​ | Green | The project status report does not indicate any need for additional staff or prioritization calls, nor does it mention any lack of resources or skills. Therefore, it is implied that existing staff can deliver the work associated with this project.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | owning_portfolio_it_resource_capacity​ | Green | The project status report does not indicate any need for additional staff or prioritization calls, nor does it mention any lack of resources or skills. Therefore, it is implied that existing staff can deliver the work associated with this project.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | ongoing_supportability_of_solution​​ | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | effective_governance​ | Red | Don't have the data to provide.
PRJ4873250 | 2025 - MACk (Movements Automatically Connected) | 2025-09-20 | partnership_and_collaboration | Red | Don't have the data to provide.