## Sheet1
Project Name | Number | Executive Summary | Planned end date | Planned start date | Updated | Phase | Business Value Comment | Comments | Comments on Budget | Comments on Cost | Comments on Resources | Comments on Schedule | Comments on Scope | Key Activities planned | Last Month's Achievements
2025 - MACk (Movements Automatically Connected) | PRJ4873250 |  | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-09-01 17:18 | Initiating
2025 - MACk (Movements Automatically Connected) | PRJ4873250 | <p><strong>Progress &amp; Successes:</strong></p> <ul style="list-style-position: inside;"><li>Carbon IQ: Went live successfully on 23rd June. Hypercare closed at the end of July.</li><li>Kendo to SDS Migration Complete on 18th July. Hypercare closed at the end of July.</li><li>Project closure in progress, planned to complete end of Aug</li></ul> <p><strong>Challenges &amp; RTG</strong>:</p> <ul style="list-style-position: inside;"><li>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</li></ul> | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-09-01 12:04 | Initiating |  | <p>NA</p> |  | <p>Cost: LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Close project and return funds.</p>
2025 - MACk (Movements Automatically Connected) | PRJ4873250 | <p><strong>Progress &amp; Successes:</strong></p> <ul style="list-style-position: inside;"><li>Carbon IQ: Went live successfully on 23rd June. Currently in hypercare through to end of July. No major issues raised, 1 bug being addressed and planned to be deployed 18th July.</li><li>Kendo to SDS Migration: 80&#43;% complete - Still on track to be fully completed in July. Deployment planned for 18th July.</li><li>Project closure planned for month of August</li></ul> <p><strong>Challenges &amp; RTG</strong>:</p> <ul style="list-style-position: inside;"><li>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</li></ul> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-08-01 12:03 | Initiating |  | <p>NA</p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> |  | <p>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p>Agreement to close the project after Carbon IQ hypercare for end of July with Project Closure in Aug </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p>
2025 - MACk (Movements Automatically Connected) | PRJ4873250 | <p><strong>Progress &amp; Successes:</strong></p> <ul style="list-style-position: inside;"><li>Carbon IQ: Integration test complete, currently in UAT with a planned go-live on 4th July.</li><li>Kendo to SDS Migration: 80&#43;% complete - Still on track to be fully completed in July.</li></ul> <p><strong>Challenges &amp; RTG</strong>:</p> <ul style="list-style-position: inside;"><li>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</li></ul> | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-07-01 12:03 | Initiating |  | <p>NA</p> |  | <p>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</p> |  |  | <p>Agreement to close the project after Carbon IQ hypercare for end of July with Project Closure in Aug </p>
2025 - MACk (Movements Automatically Connected) | PRJ4873250 |  | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-09-01 17:18 | Initiating
2025 - MACk (Movements Automatically Connected) | PRJ4873250 | <p><strong>Progress &amp; Successes:</strong></p> <ul style="list-style-position: inside;"><li>Carbon IQ: Went live successfully on 23rd June. Hypercare closed at the end of July.</li><li>Kendo to SDS Migration Complete on 18th July. Hypercare closed at the end of July.</li><li>Project closure in progress, planned to complete end of Aug</li></ul> <p><strong>Challenges &amp; RTG</strong>:</p> <ul style="list-style-position: inside;"><li>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</li></ul> | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-09-01 12:04 | Initiating |  | <p>NA</p> |  | <p>Cost: LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Close project and return funds.</p>
2025 - MACk (Movements Automatically Connected) | PRJ4873250 | <p><strong>Progress &amp; Successes:</strong></p> <ul style="list-style-position: inside;"><li>Carbon IQ: Went live successfully on 23rd June. Currently in hypercare through to end of July. No major issues raised, 1 bug being addressed and planned to be deployed 18th July.</li><li>Kendo to SDS Migration: 80&#43;% complete - Still on track to be fully completed in July. Deployment planned for 18th July.</li><li>Project closure planned for month of August</li></ul> <p><strong>Challenges &amp; RTG</strong>:</p> <ul style="list-style-position: inside;"><li>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</li></ul> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-08-01 12:03 | Initiating |  | <p>NA</p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> |  | <p>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p>Agreement to close the project after Carbon IQ hypercare for end of July with Project Closure in Aug </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p> | <p> </p> <p><span id="__symantecMPKIClientDetector" style="display: none;">__PRESENT</span></p>
2025 - MACk (Movements Automatically Connected) | PRJ4873250 | <p><strong>Progress &amp; Successes:</strong></p> <ul style="list-style-position: inside;"><li>Carbon IQ: Integration test complete, currently in UAT with a planned go-live on 4th July.</li><li>Kendo to SDS Migration: 80&#43;% complete - Still on track to be fully completed in July.</li></ul> <p><strong>Challenges &amp; RTG</strong>:</p> <ul style="list-style-position: inside;"><li>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</li></ul> | 2025-12-31 16:00 | 2025-01-20 07:00 | 2025-07-01 12:03 | Initiating |  | <p>NA</p> |  | <p>Cost (Amber): LE &amp; budget is currently showing $2m for the end of year. Completing activities 5 months earlier will result in giveback of funds - approx $0.7-$1m. RTG: Raise PCR to return funds and communicate in Steering project closure in Aug.</p> |  |  | <p>Agreement to close the project after Carbon IQ hypercare for end of July with Project Closure in Aug </p>