## Sheet1
project_id | project_name | rating_date | optic_name | rating | justification
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | firmness_of_opportunity | Red | DAF / GIP or 'one pager' not yet prepared. Approvals not expected for >3 months. Start date of IT effort unknown. There is no direct mention of DAF/GIP being prepared or internal approvals being secured, nor a known start date for IT effort in the provided project status report. Based on the criteria, the conditions match the RED rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | business_case | Red | The project status report does not provide evidence of L1 and/or L2 benefits with defined benefit owners. There are mentions of milestones and achievements, but no direct information on a defined benefits case or benefit owners. Thus, according to the criteria, it falls under 'No Benefits case developed / existing benefits no longer valid'.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | business_requirements | Red | The project status report lacks definite evidence of clearly defined and documented requirements in a Charter or similar document. Instead, the report highlights challenges such as market data agreements with ICE exchange not being confirmed, as well as resource hiring delays, indicating that the requirements are inadequately defined. Therefore, it matches the criteria for a RED rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | solution​ | Amber | While there are multiple developments and planning in place, such as the Henry Hub onboarding, scheduled feature releases, and disaster recovery exercises, there are still ongoing challenges like unresolved market data agreements with ICE and resource issues. This indicates that additional time/work is needed to fully define and solidify the solution.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | estimate_budget_accuracy​ | Green | Comments on Cost: Costs are in line with budgets. This statement indicates that the project estimates are holding within a reasonable margin of the budget, suggesting a confidence level within +/- 20%, which aligns with the criteria for a GREEN rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | commercialops_functions_support​ | Red | Additional BA & Dev need to be hired into Houston and resume quality remains unsatisfactory, this will extend times to build the team. Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. Endur resources have not arrived as anticipated as they have been prioritised by the cc onto other projects. These points highlight a lack of required skills and capabilities, matching the RED rating criteria.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | ts_and_broader_rds_it_resource_Capacity | Red | Additional BA & Dev need to be hired into Houston and resume quality remains unsatisfactory, this will extend times to build the team. Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. Endur resources have not arrived as anticipated as they have been prioritised by the cc onto other projects. These points highlight a lack of required skills and capabilities, matching the RED rating criteria.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | ts_process_team_within_comm_ops_bia_org​ | Amber | Comments on Resources: Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. This shows that additional staff is needed, which matches the criteria for an AMBER rating where additional staff needed and/or a prioritisation call is needed.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | owning_portfolio_it_resource_capacity​ | Amber | Comments on Resources: Senior Developer has started in Houston Looking to hire an additional developer and BA in Houston to support the eMarketplace work and wider DSX program adoption in US. This indicates that additional staff is needed, which matches the criteria for an AMBER rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | ongoing_supportability_of_solution​​ | Red | Global Support Model: Internal model being discussed with the IT Management. Final step is to go to Owen O'Connell in Sept for approval. This indicates that the support model is still under discussion and has not yet been approved, meeting the criteria where the support model is unclear.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | effective_governance​ | Red | The project status report does not provide any specific information that a governance model has been drafted, agreed upon, or defined across IT and Business stakeholders. Additionally, there is no mention of a decision owner being identified, which fulfills the RED rating criteria since it indicates 'Governance model not yet drafted'.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-24 | partnership_and_collaboration | Red | Business and IT teams do not have experience working together OR have experience but relationship is challenged. The project status report indicates significant challenges, such as 'Morgan Stanley (Euronext) connectivity not working and response from the bank have been lacklustre,' and issues with hiring additional BA & Dev in Houston, which impacts team collaboration efforts. This fulfills the criteria for RED as it indicates a challenged relationship.