## Sheet1
project_id | project_name | optic_name | rating_date | rating | justification | recommendation
PRJ0016435 | Downstream Exchange Product (DSX) | business_case | 2025-09-26 | Red | The project status report lacks specific information on defined benefits with agreed benefit owners. The report highlights challenges related to market data agreements and other issues impacting potential go-live dates, but there is no mention of a developed benefits case or its defined outcomes in the provided report sections. | Develop a clear benefits case with specific, agreed-upon benefit owners to transition the rating to Green. Ensure this is aligned with the project's goals and timelines, addressing any challenges that directly affect these benefits.
PRJ0016435 | Downstream Exchange Product (DSX) | business_requirements | 2025-09-26 | Amber | The project status report indicates that additional requirements gathering is needed in some portfolios. While technical and functional readiness is on track, issues related to Market Data Agreements with ICE exchange and internal reorganization affecting pilot participation suggest that some areas need further attention to formally mobilize. | To achieve a Green rating, ensure all requirements, especially related to Market Data Agreements and pilot customer participation, are comprehensively defined and documented. Address and resolve external dependencies and ensure readiness in all impacted portfolios before proceeding.
PRJ0016435 | Downstream Exchange Product (DSX) | commercialops_functions_support​ | 2025-09-26 | Amber | The project status report indicates that 'Resources (Amber): Hiring of AES tech lead remains challenging', and there is a suggestion to onboard niche recruiters. Additionally, 'RTG track progress and see if additional resources would help improve the delivery' implies that additional staff may be needed. | To achieve a Green rating, ensure all necessary staff, especially for key roles like the AES tech lead, are hired and onboarded swiftly. Consider conducting a thorough skills-gap assessment to confirm if further prioritization or resource allocation is needed to support current project commitments and timelines.
PRJ0016435 | Downstream Exchange Product (DSX) | effective_governance​ | 2025-09-26 | Amber | The report mentions that 'Global Support Model: Internal model being discussed with the IT Management. Final step is to go to Owen O'Connell in Sept for approval.' This indicates that the governance model is drafted but not yet fully agreed and final approval is still pending, which aligns with the criteria for an Amber rating. | To achieve a Green rating, expedite the agreement and approval process of the governance model with IT Management and ensure it fully addresses the project scope and risk, with clear identification of decision owners.
PRJ0016435 | Downstream Exchange Product (DSX) | estimate_budget_accuracy​ | 2025-09-26 | Red | The project status report lacks specific information related to budget estimates and their confidence levels. Without specific mention of capacity or scope-based estimates or their confidence intervals, no direct evidence can be found in the report to support a Green or Amber rating. The repeated 'Schedule (Red)' indications due to unresolved Market Data Agreements suggest ongoing issues and possible impact to costs, signifying a planning number based on little science. | To improve the rating to Green, the project team should establish a detailed capacity or scope-based budget estimate with defined confidence levels. Address any pending agreements or external dependencies impacting budget predictions and ensure a more data-driven approach to future budget estimations.
PRJ0016435 | Downstream Exchange Product (DSX) | firmness_of_opportunity | 2025-09-26 | Red | DAF / GIP or 'one pager' not yet prepared. Approvals not expected for >3 months. Start date of IT effort unknown. Schedule (Red): Externalisation: Market Data Agreements may not be agreed with ICE exchange prior to go-live. Need agreement by end of Aug if we are to stick with the go-live end of Sept. Technical & functional readiness is on track for Sept; however, significant legal and agreement details remain unresolved. | To move the rating to Green, prioritize resolving Market Data Agreements with ICE exchange, and ensure all internal approvals are fast-tracked. Establish a concrete start date for the IT effort once these approvals and agreements are secured.
PRJ0016435 | Downstream Exchange Product (DSX) | ongoing_supportability_of_solution​​ | 2025-09-26 | Red | Global Support Model: Internal model being discussed with the IT Management. Final step is to go to Owen O'Connell in Sept for approval. The support model is currently unclear as it is still under discussion and has not yet been finalized or approved, thereby resulting in an unclear support model assessment. | To move the rating to Green, prioritize the finalization and approval of the Global Support Model. Ensure it fits within an established support model or contract, such as Accenture Managed Service, to guarantee effective ongoing support for the solution.
PRJ0016435 | Downstream Exchange Product (DSX) | owning_portfolio_it_resource_capacity​ | 2025-09-26 | Amber | The report mentions 'Resources (Amber): Hiring of AES tech lead remains challenging' and suggests 'RTG track progress and see if additional resources would help improve the delivery,' implying that additional staff may be needed and/or a prioritization call is needed. | To achieve a Green rating, ensure all necessary staff, particularly for key roles like the AES tech lead, are hired and onboarded without delays. Consider conducting a skills-gap analysis to confirm if further resource allocation is needed to meet the project's current demands and maintain its timeline.
PRJ0016435 | Downstream Exchange Product (DSX) | partnership_and_collaboration | 2025-09-26 | Red | The project status report lacks direct evidence of a strong working relationship between business and IT teams or past successful collaborations. Additionally, the report does not mention any previous experience or current team building efforts to improve the relationship, indicating a lack of experience or challenged relationship. | To move the rating to Green, it's essential to enhance collaboration efforts between business and IT teams. Initiate joint team-building activities, document previous successful collaborations if any exist, and establish clear communication channels to build a strong partnership.
PRJ0016435 | Downstream Exchange Product (DSX) | solution​ | 2025-09-26 | Amber | While technical and functional readiness is on track for September and the PEN Test completed without any major or critical findings, the project still faces significant challenges. There are unresolved issues concerning the Market Data Agreements with ICE exchange critical for the go-live, and security developments are slightly behind plan, impacting the PEN test timeline. This indicates that additional time and work are needed to resolve these challenges before the solution​ can be fully defined and considered ready. | To achieve a Green rating, immediately prioritize resolving the Market Data Agreements with ICE exchange, and address any security developments impacting the PEN test timeline. Ensure all dependencies are managed and that any pilot customer participation issues are resolved promptly to keep the project on track for the planned go-live dates.
PRJ0016435 | Downstream Exchange Product (DSX) | ts_and_broader_rds_it_resource_Capacity | 2025-09-26 | Amber | The project status report discusses an 'Internal model being discussed with the IT Management.' However, it mentions 'Challenges & RTG: Resources (Amber): Hiring of AES tech lead remains challenging RTG Plan: Continue to Onboard Niche recruiters' and 'RTG track progress and see if additional resources would help improve the delivery,' indicating that requests for resources have been made but firm commitments are not evident. | To achieve a Green rating, finalize resource discussions by obtaining firm commitments from the necessary IT resources. Implement effective hiring strategies to swiftly fill key positions like the AES tech lead and ensure resource allocations are aligned with project demands and timelines.
PRJ0016435 | Downstream Exchange Product (DSX) | ts_process_team_within_comm_ops_bia_org​ | 2025-09-26 | Amber | The project status report indicates 'Resources (Amber): Hiring of AES tech lead remains challenging RTG Plan: Continue to Onboard Niche recruiters' and 'RTG track progress and see if additional resources would help improve the delivery'. This implies additional staff may be needed or a prioritization call is needed. | To achieve a Green rating, ensure all necessary staff, especially for key roles like the AES tech lead, are hired and onboarded swiftly. Consider conducting a thorough skills-gap assessment to confirm if further prioritization or resource allocation is needed to support current project commitments and timelines.
PRJ5025201 | CI Tracker Canada | business_case | 2025-09-26 | Red | The project status report lacks any mention of defined L1 and/or L2 benefits, agreed benefit owners, or a benefits case. The sections provided do not offer any direct evidence of a benefits case being developed or that existing benefits are defined, which places this under the 'RED' category due to the criteria stating 'No Benefits case developed / existing benefits no longer valid'. | Develop a comprehensive benefits case including defined benefits and owners to align the project with strategic objectives and meet 'GREEN' criteria. This will help ensure the project delivers value and justifies the investment.
PRJ5025201 | CI Tracker Canada | business_requirements | 2025-09-26 | Green | The project status report indicates that 'Completed requirement, scoping and got sign off - 13th Aug'. This statement confirms that requirements for impacted portfolios are clearly defined and documented, fulfilling the criteria for a 'GREEN' rating. | Maintain the documentation of the requirements and ensure continuous alignment with the project scope as development progresses. Regular review and validation of the requirements with stakeholders will help sustain the Green rating.
PRJ5025201 | CI Tracker Canada | commercialops_functions_support​ | 2025-09-26 | Green | The project status report indicates that there are no challenges ('Challenges & RTG: None') and no comments on resources, schedule, cost, or any other section that would suggest a need for additional staff or prioritization. This implies that existing staff can deliver all necessary work. | Continue with the current staffing levels, ensuring that any emerging resource needs are addressed promptly to maintain the efficient delivery of project objectives. Regular monitoring of team workload and capacity will help sustain the Green rating.
PRJ5025201 | CI Tracker Canada | effective_governance​ | 2025-09-26 | Red | The project status report lacks any mention of a governance model being defined, drafted, or agreed upon. There is no evidence of a governance model that addresses the project scope and risk, nor is there a clear decision owner identified. Consequently, this aligns with the 'RED' category where the governance model is not yet drafted. | It is essential to develop a comprehensive governance model that is agreed upon by both IT and Business stakeholders, addressing the project's scope and risk. Identify a clear decision owner to ensure effective governance and shift the rating to 'GREEN'. This will improve strategic decision-making and project oversight.
PRJ5025201 | CI Tracker Canada | estimate_budget_accuracy​ | 2025-09-26 | Red | The project status report does not contain any direct information regarding budget estimates or the level of confidence about budget estimates. Comments on budget, cost, resources, and schedule are all either empty or contain dashes, indicating a lack of detailed information. Consequently, this suggests a planning number based on little science, aligning with the 'RED' rating. | It is critical to develop a detailed budget estimate with a quantified level of confidence. Project management should prioritize creating a capacity or scope-based estimate with sufficient detail to achieve at least a 'GREEN' or 'AMBER' rating. This will facilitate better financial planning and risk management moving forward.
PRJ5025201 | CI Tracker Canada | firmness_of_opportunity | 2025-09-26 | Green | The project status report indicates that requirements and scoping were completed and signed off on August 13th. The design was also completed and signed off on the same date. Additionally, the statement 'Currently in iterative development for MVP (U/Prog), Started development for DEAL GUI Changes' and 'Started Regression testing, planned to complete Fri 26th Sept' imply that the start date of IT effort is known and the project is well underway without any mentioned challenges. | Continue monitoring the project to ensure all internal approvals remain valid as the project progresses. Maintain communication with all impacted portfolios to promptly address any emerging issues and sustain the Green rating.
PRJ5025201 | CI Tracker Canada | ongoing_supportability_of_solution​​ | 2025-09-26 | Red | The project status report does not provide any information about the support model for the solution. There is no mention of an existing support model or contract, amendments needed, or plans for a new support arrangement. Therefore, this aligns with the 'RED' category where the support model is unclear. | Clarify support requirements by reviewing the solution's fit within existing models or determine if a new support framework is needed. Establish clear support mechanisms to enhance the solution's supportability rating.
PRJ5025201 | CI Tracker Canada | owning_portfolio_it_resource_capacity​ | 2025-09-26 | Green | The project status report lists no comments about current resource challenges or needs, and there are no additional staff requirements or prioritization calls mentioned. The section 'Challenges & RTG' mentions 'None', indicating that existing staff can deliver the work, aligning with the 'GREEN' criteria. | Continue monitoring to ensure the staff capacity remains sufficient as the project progresses and that potential resource changes are addressed proactively to maintain the Green rating.
PRJ5025201 | CI Tracker Canada | partnership_and_collaboration | 2025-09-26 | Red | The project status report lacks direct evidence of past collaboration experience or a solid working relationship between Business and IT teams. There are no statements referring to any experience working together or the quality of their relationship, which aligns with the 'RED' criteria: 'Business and IT teams do not have experience working together OR have experience but relationship is challenged'. | It is crucial to facilitate initial team-building activities to encourage collaboration and establish a strong working relationship between Business and IT teams. Developing a mutual understanding of goals and expectations will help transition this rating to 'AMBER' or 'GREEN'.
PRJ5025201 | CI Tracker Canada | solution​ | 2025-09-26 | Green | The project status report indicates 'Completed requirement, scoping and got sign off - 13th Aug' and 'Completed Design and sign off - 13th Aug'. Additionally, 'Currently in iterative development for MVP (U/Prog), Started development for DEAL GUI Changes' demonstrates that the solution is well-defined and understood, ready for mobilization. No challenges are mentioned, supporting the solution's readiness. | Proceed with the current development phases and maintain regular progress checks to ensure that the solution remains aligned with the project objectives. Continue to document any changes or updates to the solution to preserve the Green rating.
PRJ5025201 | CI Tracker Canada | ts_and_broader_rds_it_resource_Capacity | 2025-09-26 | Amber | The project status report lacks explicit mentions of resource discussion outcomes or commitments. Sections such as 'Comments on Resources' are empty, and there are no direct quotes that confirm resource commitments. The absence of firm commitments places this in the 'AMBER' category as per the criteria: 'Request made, no firm commitments made'. | Engage with relevant stakeholders to secure firm resource commitments. This will ensure that the project has the necessary resources to proceed without risking delays or capability gaps. Formalizing these commitments can shift the rating to 'GREEN'.
PRJ5025201 | CI Tracker Canada | ts_process_team_within_comm_ops_bia_org​ | 2025-09-26 | Green | The project status report indicates 'Challenges & RTG: None', and there are no comments on resources needed, suggesting that the existing staff can deliver the work without additional external resources, aligning with the criteria for a 'GREEN' rating. | Continue monitoring project progress to ensure that staffing remains adequate and promptly address any future resource needs to maintain the Green rating. Regular updates and capacity checks should be conducted to sustain operational efficiency throughout the project.