## Sheet1
project_id | project_name | rating_date | optic_name | rating | justification
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | firmness_of_opportunity | Red | DAF / GIP or 'one pager' not yet prepared. Approvals not expected for >3 months. Start date of IT effort unknown
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | business_case | Amber | There is mention that 'Pilot customer may not be able to participate as internal reorg is taking their focus, still planned to show by end of Aug the demo. Alternative customers identified for pilot if required.' This suggests ongoing work on business case issues as the original benefits case related to the pilot customer needs revisiting and alternative strategies are being considered.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | business_requirements | Red | Inadequately defined requirements. The project status report does not mention any clear definition or documentation of requirements for impacted portfolios. The focus is on technical and scheduling challenges.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | solution​ | Amber | There is mention in multiple sections that additional work and final approvals are still needed. Specifically, the 'Challenges & RTG' section notes 'Market Data Agreements may not be agreed with ICE exchange prior to go-live' and 'Legal drafting a letter to reinstate ask', which indicates that the solutions have not been fully understood or agreed upon. The unresolved legal and market data agreement suggests that the solution is not yet fully defined, requiring additional work.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | estimate_budget_accuracy​ | Red | There is no direct evidence in the project status report indicating a capacity or scope-based estimate with a specific confidence level. The report discusses schedule and externalization challenges, such as 'Schedule (Red): Externalisation: Market Data Agreements may not be agreed with ICE exchange prior to go-live' and 'Legal drafting a letter to reinstate ask,' which implies a high level of uncertainty, consistent with a planning number based on little science with +/- 50% level of confidence.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | commercialops_functions_support​ | Amber | The executive summary mentions that 'Global Support Model: Internal model being discussed with the IT Management,' indicating that there may be ongoing discussions on support needs and possibly additional staff requirements. No evidence suggests a current lack of required skills, but the need for additional or prioritization suggests an Amber rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | ts_and_broader_rds_it_resource_Capacity | Amber | The executive summary states: 'Global Support Model: Internal model being discussed with the IT Management. Final step is to go to Owen O'Connell in Sept for approval.' This suggests that discussions have taken place, but no firm commitments have been made. The current status aligns with the criteria for Amber: 'Request made, no firm commitments made.​'
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | ts_process_team_within_comm_ops_bia_org​ | Green | There is no mention in the project status report that additional staff or specific prioritisation calls are needed. The achievements and progress sections indicate ongoing developments and deployments without direct evidence of resource shortages or skill gaps, thus satisfying the criteria that 'Existing staff can deliver the work.'
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | owning_portfolio_it_resource_capacity​ | Green | The project status report does not explicitly mention any lack of resources or skill gaps that would hinder the current progress. All scheduled activities and achievements describe successful deployments and protected timelines, implying that the current staffing suffices to deliver the work, satisfying the criteria for a Green rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | ongoing_supportability_of_solution​​ | Amber | The project status report states: 'Final step is to go to Owen O'Connell in Sept for approval.' Additionally, 'Global Support Model: Internal model being discussed with the IT Management,' indicates that amendments to an existing support model / contract or new support requirements are potentially being considered and are in scope for delivery, suggesting an Amber rating.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | effective_governance​ | Red | There is no direct evidence in the project status report of a governance model being defined, agreed across stakeholders, or even drafted. The absence of mention regarding a governance model indicates that it has not yet been drafted.
PRJ0016435 | Downstream Exchange Product (DSX) | 2025-09-19 | partnership_and_collaboration | Red | The project status report does not mention any prior collaborations or established relationships between the Business and IT teams. Furthermore, there is no evidence of a strong working relationship or past project deliveries together, and there are no specifics on team building or relationship improvement activities required, leading to the default assumption that the relationship is not well-established.