## Sheet1
Project Name | Number | Portfolio manager | Executive Summary | Planned end date | Planned start date | Updated | Phase | Business Value Comment | Comments | Comments on Budget | Comments on Cost | Comments on Resources | Comments on Schedule | Comments on Scope | Key Activities planned | Last Month's Achievements
2025 HVO B7 - LCF IDT | PRJ4872962 | Sandeep Satapathy (GBSSBW) | test1 | 2026-01-12 17:00 | 2025-01-17 08:00 | 2025-09-01 17:29 | Closing
2025 HVO B7 - LCF IDT | PRJ4872962 | Sandeep Satapathy (GBSSBW) | <p><span style="font-size: 10pt;"><strong>Progress &amp; Success:</strong></span></p> <ul style="list-style-position: inside;"><li style="font-size: 10pt;">Hypercare successfully completed and ATO signed-off as per plan. Project team dispersed. Closure activities are in progress.</li><li style="font-size: 10pt;">The &#39;HVO B7&#39; tool is projected to generate approximately $3 million per annum in tax rebates for Shell, with the value poised to grow as sales of HVO B7 continue to increase.</li></ul> <p><span style="font-size: 10pt;"><strong>Challenges &amp; RTGs:</strong></span></p> <ul style="list-style-position: inside;"><li style="font-size: 10pt;">None</li></ul> | 2026-01-12 17:00 | 2025-01-17 08:00 | 2025-09-01 12:02 | Planning |  | <ul style="list-style-position: inside;"><li style="font-size: 10pt;"><span style="font-size: 10pt;">Once the data in AMDP production is fixed. AMDP team will inform and work with T&amp;S support to make the appropriate changes in the HVO B7 code to start consuming data from AMDP. Project team already provided hand over to the support team regarding the changes they need to make. </span><br /><br /></li></ul> | [5 empty] | <ul style="list-style-position: inside;"><li style="font-size: 10pt;">To close the project in SNOW. </li></ul> | <ul style="list-style-position: inside;"><li style="font-size: 10pt;"><span style="font-size: 13.3333px;">Hypercare successful completed, after receiving sign-off from Business. </span></li></ul>
2025 HVO B7 - LCF IDT | PRJ4872962 | Sandeep Satapathy (GBSSBW) | <p><span style="font-size: 10pt;"><strong>Progress &amp; Success:</strong></span></p> <ul style="list-style-position: inside;"><li style="font-size: 10pt;">Successful cutover and go-live on 3rd July. Currently in hypercare until 31st of July. No issues raised. The &#39;HVO B7&#39; tool is projected to generate approximately $3 million per annum in tax rebates for Shell, with the value poised to grow as sales of HVO B7 continue to increase.</li></ul> <p><span style="font-size: 10pt;"><strong>Challenges &amp; RTGs:</strong></span></p> <ul style="list-style-position: inside;"><li style="font-size: 10pt;">None</li></ul> | 2026-01-12 17:00 | 2025-01-17 08:00 | 2025-08-01 12:03 | Planning |  | <ul style="list-style-position: inside;"><li>Chemical and Products team is working on fixing the Asset Management Data Platform prod issue. <br />• UAT is progressing as per plan, targeted to be completed by June 20th. </li></ul> | [5 empty] | <ul style="list-style-position: inside;"><li style="font-size: 10pt;">AMDP team to fix the data issue at their end for providing OMM data to the B7 project team to consume in production. </li><li style="font-size: 10pt;">Successfully conclude User Acceptance Testing by June 20th, according to the schedule.<br />• Secure ATD and raise change request for prod deployment. <br />• Initiate production cutover activities with the support team by executing the deployment plan.<br />• Provide the deployment scripts to the support team, once the final UAT sign-off is secured. <br />• Coordinate with various IDSO teams to ensure readiness for production deployment.</li></ul> | <ul style="list-style-position: inside;"><li style="font-size: 10pt;">Secured partial sign-off for the frontend i.e. UI &amp; UX. The final UAT sign-off to be received once the backend test cases are completed. </li><li style="font-size: 10pt;">Technical documentation has been finalized and shared with the support team, enhancing project readiness. <br /><span style="font-size: 10pt;">• Knowledge transfer sessions with the support team have been completed.</span><br /><span style="font-size: 10pt;">• A baseline user manual has been shared with the business team.<span style="font-family: verdana, geneva;"> </span></span></li><li style="font-size: 10pt;">Deployment plan shared and agreed with the support team.</li></ul>
2025 HVO B7 - LCF IDT | PRJ4872962 | Sandeep Satapathy (GBSSBW) | <p><span style="font-size: 10pt;"><strong>Progress &amp; Success:</strong></span></p> <ul style="list-style-position: inside;"><li style="font-size: 10pt;">UAT is progressing as per plan (approx. 95% completed so far). UAT test cases (Data validation) execution is ongoing, and the development team is working on addressing defect/bug fixes. We aim to complete User Acceptance Testing (UAT) by June 20th, unless we encounter any bug/defect that may require additional time to resolve. Once we receive the final UAT sign-off, we will kick off the production cutover activities. As it stands, we are on track to go live during the week of June 30th. </li></ul> <p><span style="font-size: 10pt;"><strong>Challenges &amp; RTGs:</strong></span></p> <ul style="list-style-position: inside;"><li style="font-size: 10pt;">Schedule (AMBER): The project status has shifted to Amber due to a dependency on the Asset Management Data Platform (AMDP), managed by the Chemicals &amp; Products CoB team, which is currently experiencing data discrepancy issues with the OMM data in Production. The Chemicals &amp; Products IDT team is actively working with the OMM and PCD teams to resolve these issues and ensure accurate data flow from OMM to AMDP for HVO B7. If the data discrepancies in AMDP production are not resolved before the planned go-live date we will delay the go-live.</li></ul> | 2026-01-12 17:00 | 2025-01-17 08:00 | 2025-07-01 12:03 | Planning |  | <ul style="list-style-position: inside;"><li style="font-size: 10pt;">Chemical and Products team is working on fixing the Asset Management Data Platform prod issue. <br />• UAT is progressing as per plan, targeted to be completed by June 20th. </li></ul> |  |  | <p><span style="font-size: 10pt;">Worked with CC team and m</span><span style="font-size: 10pt;">anaged to retain the primary data engineer to continue work on the project, hence the associated risk is mitigated now and Resourcing status moved back to Green. </span></p> | <p><span style="font-size: 10pt;">Challenge: The project has transitioned to an Amber status due to its dependency on the Asset Management Data Platform (AMDP), which is managed by the Chemicals &amp; Products CoB team. Currently, they are experiencing discrepancies with the OMM production data in AMDP. </span></p> <p><span style="font-size: 10pt;">Return to Green: The Chemicals &amp; Products IDT team is collaborating with the OMM and PCD teams to address the prod issue and ensure that the correct data flows from OMM to AMDP, enabling HVO B7 to function properly - Commitment for the fix to be in place by 25th June.</span></p> <p><span style="font-size: 10pt;">If the data in the AMDP production environment is not corrected before our planned go-live date, it will impact the project&#39;s schedule.</span></p> <p> </p> |  | <ul style="list-style-position: inside;"><li style="font-size: 10pt;">AMDP team to fix the data issue at their end for providing OMM data to the B7 project team to consume in production. </li><li style="font-size: 10pt;">Successfully conclude User Acceptance Testing by June 20th, according to the schedule.<br />• Secure ATD and raise change request for prod deployment. <br />• Initiate production cutover activities with the support team by executing the deployment plan.<br />• Provide the deployment scripts to the support team, once the final UAT sign-off is secured. <br />• Coordinate with various IDSO teams to ensure readiness for production deployment.</li></ul> | <ul style="list-style-position: inside;"><li style="font-size: 10pt;"><span style="font-size: 10pt;">Secured partial sign-off for the frontend i.e. UI &amp; UX. The final UAT sign-off to be received once the backend test cases are completed. </span></li><li style="font-size: 10pt;"><span style="font-size: 10pt;">Technical documentation has been finalized and shared with the support team, enhancing project readiness. </span><br /><span style="font-size: 10pt;">• Knowledge transfer sessions with the support team have been completed.</span><br /><span style="font-size: 10pt;">• A baseline user manual has been shared with the business team.<span style="font-family: verdana, geneva;"> </span></span></li><li style="font-size: 10pt;"><span style="font-size: 10pt;">Deployment plan shared and agreed with the support team.</span></li></ul>
2025 Planning and Scheduling IDT Work | PRJ4897790 | Sandeep Satapathy (GBSSBW) | <p><span style="font-size: 10pt;"><strong>Progress &amp; Success:</strong></span></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Negotiations with Kinaxis on licenses is near completion, work is in progress on the timeline and cost for the blueprinting, design &amp; detailed planning phase.</li><li style="font-size: 10pt;">IDT &amp; Business cost estimates have been completed for the GIP. </li><li style="font-size: 10pt;">IDT detailed design work on integration between Planning &amp; Scheduling and source systems (GSAP, DEX, etc.) is on track. planned to complete end of Sep&#39;25.​</li></ul> <p><span style="font-size: 10pt;"><strong>Challenges &amp; RTG Plans:</strong></span></p>fsfa <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Schedule (AMBER): DRB has asked to target end of July for GIP signoff, so that the contract with Kinaxis could be signed ASAP. GIP has been delayed by one month, revised date is now end of Aug. RTG: Planned dates are aligned with business stakeholders. Final signature is with Richard Jory.</li><li style="font-size: 10pt;">Cost (RED): $750k budget approved through to the end of July has been spent. RTG: Sandeep to request bridge funding of $250k cover until end of Sep&#39;25 and GIP approval.</li><li. style="font-size: 10pt;">Value (AMBER): GIP is in draft, IT costs and plans developed, business still refining the actual value case, one month behind plan. RTG: Plan to complete and sign-off GIP by end of Aug, aligned with key business stakeholders.</li></ul> | 2027-03-31 17:00 | 2025-01-29 08:00 | 2025-09-01 06:11 | Initiating |  | <p><span style="font-size: 10pt;"><strong>Progress &amp; Success:</strong></span></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Negotiations with Kinaxis on licenses is near completion, work is in progress on the timeline and cost for the blueprinting, design &amp; detailed planning phase.</li><li style="font-size: 10pt;">IDT &amp; Business cost estimates have been completed for the GIP. </li><li style="font-size: 10pt;">IDT detailed design work on integration between Planning &amp; Scheduling and source systems (GSAP, DEX, etc.) is on track. planned to complete end of Sep&#39;25.​</li></ul> <p><span style="font-size: 10pt;"><strong>Challenges &amp; RTG Plans:</strong></span></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Schedule (AMBER): DRB has asked to target end of July for GIP signoff, so that the contract with Kinaxis could be signed ASAP. GIP has been delayed by one month, revised date is now end of Aug. RTG: Planned dates are aligned with business stakeholders. Final signature is with Richard Jory.</li><li style="font-size: 10pt;">Cost (RED): $750k budget approved through to the end of July has been spent. RTG: Sandeep to request bridge funding of $250k cover until end of Sep&#39;25 and GIP approval.</li><li style="font-size: 10pt;">Value (AMBER): GIP is in draft, IT costs and plans developed, business still refining the actual value case, one month behind plan. RTG: Plan to complete and sign-off GIP by end of Aug, aligned with key business stakeholders.</li></ul> |  | <p> $750k budget approved through to the end of July has been spent. RTG: Sandeep to request bridge funding of $250k cover until end of Sep&#39;25 and GIP approval.</p> |  | <p>DRB has asked to target end of July for GIP signoff, so that the contract with Kinaxis could be signed ASAP. GIP has been delayed by one month, revised date is now end of Aug. RTG: Planned dates are aligned with business stakeholders. Final signature is with Richard Jory.</p>
2025 Planning and Scheduling IDT Work | PRJ4897790 | Sandeep Satapathy (GBSSBW) | <p><span style="font-size: 10pt;"><strong>Progress &amp; Success:</strong></span></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;"><span style="font-size: 10pt;">Negotiations with Kinaxis on licenses is near completion, work is in progress on the timeline and cost for the blueprinting, design &amp; detailed planning phase.</span></li><li style="font-size: 10pt;"><span style="font-size: 10pt;">IDT &amp; Business cost estimates have been completed for the GIP. </span></li><li style="font-size: 10pt;"><span style="font-size: 10pt;">IDT detailed design work on integration between Planning &amp; Scheduling and source systems (GSAP, DEX, etc.) is on track. planned to complete end of Sep&#39;25.​</span></li></ul> <p><span style="font-size: 10pt;"><strong>Challenges &amp; RTG Plans:</strong></span></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;"><span style="font-size: 10pt;">Schedule (AMBER): DRB has asked to target end of July for GIP signoff, so that the contract with Kinaxis could be signed ASAP. GIP has been delayed by one month, revised date is now end of Aug. RTG: Planned dates are aligned with business stakeholders. Final signature is with Richard Jory.</span></li><li style="font-size: 10pt;"><span style="font-size: 10pt;">Cost (RED): $750k budget approved through to the end of July has been spent. RTG: Sandeep to request bridge funding of $250k cover until end of Sep&#39;25 and GIP approval.</span></li><li style="font-size: 10pt;"><span style="font-size: 10pt;">Value (AMBER): GIP is in draft, IT costs and plans developed, busffiness still refining the actual value case, one month behind plan. RTG: Plan to complete and sign-off GIP by end of Aug, aligned with key business stakeholders.</span></li></ul> | 2026-12-31 17:00 | 2025-01-29 08:00 | 2025-09-01 12:04 | Initiating |  | <p>Progress &amp; Success:</p> <ul style="list-style-position: inside;" type="disc"><li>Negotiations with Kinaxis: DRB confirmed walk-away points. Negotiations ongoing and expected to complete by end of July.</li><li>Progress: IDT Cost estimates are drafted and being reviewed by the IT LTs, planned to complete by end of 18th July. </li><li>IDT detailed design work on integration between Planning &amp; Scheduling and source systems (GSAP, DEX, etc.) is on track. planned to complete end of Sep&#39;25.​</li></ul> <p>Challenges &amp; RTG Plans:</p> <ul style="list-style-position: inside;" type="disc"><li>Schedule (AMBER): DRB has asked to target end of July for GIP signoff. This target date is at risk, because the commercial negotiation is taking longer than anticipated and GIP approval likely to go into Aug &#39;25 as it needs Andrew Smith&#39;s approval.</li><li>Cost (RED): $750k funding approved for the first 7 months of 2025 but initial stage will continue to the end of Q3, RTG: Sandeep to provide additional budget $250k cover until end of Sep&#39;25 and GIP approval.</li><li>Value (AMBER): 31 m$ / year level 1/level 2 Europe benefits were confirmed, down from 55 m$/year. RTG: Group Investment Proposal (GIP) to be developed and signed-off as soon as possible based on Europe business case</li></ul> |  | <p> $750k budget approved through to the end of July has been spent. RTG: Sandeep to request bridge funding of $250k cover until end of Sep&#39;25 and GIP approval.</p> |  | <p>DRB has asked to target end of July for GIP signoff, so that the contract with Kinaxis could be signed ASAP. GIP has been delayed by one month, revised date is now end of Aug. RTG: Planned dates are aligned with business stakeholders. Final signature is with Richard Jory.</p>
2025 Planning and Scheduling IDT Work | PRJ4897790 | Sandeep Satapathy (GBSSBW) | <p><strong><span style="font-size: 10pt;">Progress &amp; Success:</span></strong></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Negotiations with Kinaxis: DRB confirmed walk-away points. Negotiations ongoing and expected to complete by end of July.</li><li style="font-size: 10pt;">Progress: IDT Cost estimates are drafted and being reviewed by the IT LTs, planned to complete by end of 18th July. </li><li style="font-size: 10pt;">IDT detailed design work on integration between Planning &amp; Scheduling and source systems (GSAP, DEX, etc.) is on track. planned to complete end of Sep&#39;25.​</li></ul> <p><strong><span style="font-size: 10pt;">Challenges &amp; RTG Plans:</span>da</strong></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;"><span style="font-size: 10pt;">Schedule (AMBER): DRB has asked to target end of July for GIP signoff. This target date is at risk, because the commercial negotiation is taking longer than anticipated and GIP approval likely to go into Aug &#39;25 as it needs Andrew Smith&#39;s approval.</span></li><li style="color: rgb(0, 0, 0); font-size: 10pt;"><span style="font-size: 10pt;">Cost (RED): $750k funding approved for the first 7 months of 2025 but initial stage will continue to the end of Q3, RTG: Sandeep to provide additional budget $250k cover until end of Sep&#39;25 and GIP approval.</span></li><li style="font-size: 10pt; text-align: left;">Value (AMBER): 31 m$ / year level 1/level 2 Europe benefits were confirmed, down from 55 m$/year. RTG: Group Investment Proposal (GIP) to be developed and signed-off as soon as possible based on Europe business case</li></ul> | 2026-12-31 17:00 | 2025-01-29 08:00 | 2025-08-01 12:03 | Initiating |  | <p><strong><span style="font-size: 10pt;">Progress &amp; Success:</span></strong></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Negotiations with Kinaxis: DRB confirmed walk-away points. Negotiations ongoing and expected to complete by end July.</li><li style="font-size: 10pt;">GIP Signoff : Target to sign-off by end July is at risk. IDT Cost estimates are being reviewed. Preliminary NPV calculations are less attractive than previously assumed as the expected value has gone down and the IDT cost &amp; contingency have gone up.​</li><li style="font-size: 10pt;">IDT design work on integration between Planning &amp; Scheduling and source systems (GSAP, DEX, etc) is on track. ​</li><li style="font-size: 10pt;">$750k budget available for H1 2025. Additional short-term budget required for Q3. Full budget requirements to be confirmed after completing the vendor negotiations.​</li></ul> <p><strong><span style="font-size: 10pt;">Challenges &amp; RTG Plans:</span></strong></p> <ul style="list-style-position: inside; list-style-type: disc;"><li style="font-size: 10pt;">Schedule (AMBER): DRB has asked to target end of July for GIP signoff. This target date is at risk, because the commercial negotiation is taking longer than anticipated.</li><li style="font-size: 10pt;">Cost (RED): $750k funding approved for the first 6 months of 2025 but initial stage will continue into Q3, RTG: Sandeep to provide additional budget to cover Q3.</li></ul> <ul style="list-style-position: inside; list-style-type: disc; font-size: 10pt;" type="disc"><li style="font-size: 10pt;">Value (AMBER): 31 m$ / year level 1/level 2 benefits were confirmed, down from 55 m$/year. RTG: Group Investment Proposal (GIP) to be developed and signed-off as soon as possible based on Europe business case <p> </p> </li></ul> |  | <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Cost (RED): $750k funding approved for the first 6 months of 2025 but initial stage will continue into Q3, RTG: Sandeep to provide additional budget $250k cover until end of Sep&#39;25 and GIP approval.</li></ul> |  | <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Schedule (AMBER): DRB has asked to target end of July for GIP signoff. This target date is at risk, because the commercial negotiation is taking longer than anticipated and GIP approval likely to go into Aug &#39;25 as it needs Andrew Smith&#39;s approval.</li></ul>
2025 Planning and Scheduling IDT Work | PRJ4897790 | Sandeep Satapathy (GBSSBW) | <p><strong><span style="font-size: 10pt;">Progress &amp; Success:</span></strong></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Contract negotiations have started and are now expected to complete by end of July. After initial negotiations with Kinaxis we have seen improvements from their RFP proposal in areas relating to license costs and expansion costs</li><li style="font-size: 10pt;">Project being re-planned based on new target date for GIP signoff (End July)</li><li style="font-size: 10pt;">Good progress on the Design of the integration with the source systems (Data solution)</li><li style="font-size: 10pt;">DRB agreed to restrict scope to Europe only. Option to scale to the rest of the world.</li></ul> <p><strong><span style="font-size: 10pt;">Challenges &amp; RTG Plans:</span></strong></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Value (AMBER): 55 – 72 m$ / year European business case was signed off by senior business leaders. <p style="margin: 0cm; font-size: 11pt; font-family: Aptos, sans-serif;">RTG: Group Investment Proposal (GIP) to be developed and signed-off by end of July</p> </li><li style="font-size: 10pt;">Schedule (AMBER): Delay to original plan to have contract with vendor in place. DRB recognise and support</li><li style="font-size: 10pt;">Cost (AMBER): $750k funding approved for the first 6 months of 2025 but initial stage will continue into Q3, RTG: request from Sandeep and Cao to have GP and PDS council sign-off in July for the European Project full scope. <p style="margin: 0cm; font-size: 11pt; font-family: Aptos, sans-serif;"> </p> </li></ul> | 2025-12-31 17:00 | 2025-01-29 08:00 | 2025-07-01 12:03 | Initiating |  | <p><strong><span style="font-size: 10pt;">Progress &amp; Success:</span></strong></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 10pt;">Contract negotiations have started and are now expected to complete by end of July. After initial negotiations with Kinaxis we have seen improvements from their RFP proposal in areas relating to license costs and expansion costs</li><li style="font-size: 10pt;">Project being re-planned based on new target date for GIP signoff (to be confirmed)</li><li style="font-size: 10pt;">Good progress on the Design of the integration with the source systems (Data solution) Target to start development 1st July.</li></ul> <p><strong><span style="font-size: 10pt;">Challenges &amp; RTG Plans:</span></strong></p> <ul style="list-style-position: inside;" type="disc"><li style="font-size: 11pt; font-family: Aptos, sans-serif;">Scope (AMBER): Clarity required on EU vs Global scope. There is high confidence the current solution based on Europe scope can be scaled to NA and East, detailed process study &amp; confirmation is not expected before the end of 2025. The Europe implementation, which was planned to start in Q4 2025, will be delayed if this confirmation is a pre-requisite for signing the Kinaxis contract. <p style="margin: 0cm; font-size: 11pt; font-family: Aptos, sans-serif;"> RTG: Escalate to DRB on June 4th; DRB to decide between 2 options </p> <p style="margin: 0cm; font-size: 11pt; font-family: Aptos, sans-serif;"> 1) Proceed with Europe now</p> <p style="margin: 0cm; font-size: 11pt; font-family: Aptos, sans-serif;"> 2) Delay Europe to confirm scalability to NA / East </p> </li><li style="font-size: 10pt;">Value (AMBER): 55 – 72 m$ / year European business case was signed off by senior business leaders. <p style="margin: 0cm; font-size: 11pt; font-family: Aptos, sans-serif;"> RTG: Global Investment Proposal (GIP) to be developed and signed-off as soon as possible.</p> </li><li style="font-size: 10pt;">Schedule (RED): Based on current negotiations, headline size will be greater than $20M, GIP required before signing contract. Team started drafting GIP which needs to be completed before contract can be signed. Expected to delay signing by 2-3 months. RTG : Escalate to DRB; Request support for an accelerated signoff timeline. Due date - June 4th</li><li style="font-size: 10pt;">Cost (AMBER): $750k funding approved for the first 6 months of 2025 but initial stage will continue into Q3, RTG: CR to be raised and approved in DRB for funding through to GIP &amp; Vendor negotiation completion. <p style="margin: 0cm; font-size: 11pt; font-family: Aptos, sans-serif;"> </p> </li></ul> |  | <p>$750k funding approved for the first 6 months of 2025 but initial stage will continue into Q3, RTG: request from Sandeep and Cao to have GP and PDS council sign-off in July for the European Project.</p> | <p>Development on hold in July</p> | <p>Based on current negotiations, headline size will be greater than $20M, GIP required before signing contract. Team started drafting GIP which needs to be completed before contract can be signed. DRB has asked to target emd of July for GIP</p> <p>RTG : Seek support from DRB members to accelerate process &amp; steps</p> | <p>DRB agreed to restrict scope to Europe only. Option to scale to the rest of the world.</p>