## Sheet1
project_id | project_name | optic_name | rating_date | rating | justification | recommendation
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | business_case | 2025-09-28 | Red | There is no evidence provided in the project status report that a benefits case has been developed, nor are there any mentions of defined benefits with agreed benefit owners. The report primarily highlights operational issues and completion status without addressing the benefits explicitly. | To improve the rating to Green, it is necessary to develop a clear benefits case with defined L1 and/or L2 benefits, and ensure agreement with identified benefit owners. Revisiting or enhancing the current benefits framework could also help shift the status from Red towards Green.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | business_requirements | 2025-09-28 | Amber | The report indicates that 'All remaining work [is] clearly defined and assigned,' but also notes that 'T-Sys PM late in submitting CR, partially due to misalignment on CR approval' and 'customer wanted more time to review before giving project closure approval.' This suggests that while some requirements are clearly outlined, there is additional gathering needed due to delays and misalignment. | To achieve a Green rating, ensure all impacted portfolios have thoroughly defined and documented requirements, and resolve any outstanding misalignments or delays in requirement approvals. Enhance coordination among stakeholders to finalize requirements comprehensively.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | commercialops_functions_support​ | 2025-09-28 | Amber | Justification is evident with the comments noted in the status report stating, 'DBA team was able to provide weekend contacts to provide assistance if needed,' and the concern about weekend coverage for migrations, indicating that additional staff or prioritization might be needed for certain support requirements. | To achieve a Green rating, ensure existing staffing levels are sufficient by addressing the noted concerns regarding weekend coverage and any potential support planning issues. Consider conducting a resource assessment to identify and resolve possible staffing gaps or prioritize tasks to optimize resource allocation effectively.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | effective_governance​ | 2025-09-28 | Red | The project status report lacks direct evidence of a defined and agreed governance model across IT and business stakeholders. There is no mention of a governance model drafted or agreed upon, nor is there a clear decision owner identified. | To achieve a Green rating, a comprehensive governance model must be developed, clearly addressing the project scope and risks. It should be agreed upon by IT and business stakeholders, with a clear decision owner identified to oversee governance processes.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | estimate_budget_accuracy​ | 2025-09-28 | Red | The project status report contains several references highlighting budget challenges: the need to increase the budget due to additional work required ('CR requested to extend project end date and budget increase to cover additional work'), and mentions of budget exhaustion ('Project budget exhausted') and cost increase requests ('CR request sent to Shell, cost increase included'). These evidences suggest that the estimates were based on little science with a +/- 50% confidence level. | To improve the rating, it is essential to develop a more structured capacity or scope-based estimate with a higher confidence level. Review the project's budgetary projections, and ensure detailed and data-driven estimations that can handle potential project scope changes and extensions. Establish consistent budget monitoring practices to ensure alignment with project progress.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | firmness_of_opportunity | 2025-09-28 | Red | There is no direct evidence from the project status report that a DAF / GIP or 'one pager' is prepared, and approvals are not mentioned. Furthermore, there is no clear start date for the IT effort. The comments across the report focus on operational and completion-related details rather than planning, approvals, or IT effort start dates. | To improve the rating to Green, there is a need to prepare the DAF / GIP or 'one pager', obtain all necessary internal approvals from impacted portfolios, and establish a clear start date for the IT effort. Coordination with all stakeholders to finalize these aspects is crucial.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | ongoing_supportability_of_solution​​ | 2025-09-28 | Red | The project status report does not provide direct evidence of a clear support model or existing support contracts, nor does it mention a continuous delivery (DevOps) model that already exists. Instead, statements such as 'only as needed support' and concerns about 'weekend coverage for migrations' indicate unclear or ad hoc support planning. | To improve the rating to Green, establish a clearly defined support model incorporated within an existing contract, such as an Accenture Managed Service. Ensure comprehensive support planning is in place, with formal agreements that cover all necessary requirements, including weekend and short-term support needs.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | owning_portfolio_it_resource_capacity​ | 2025-09-28 | Amber | The report highlights concerns related to staffing resources: 'some concern on weekend coverage for migrations,' and also mentions, 'Lowlights- short notice given on needed support cause support planning issues.' This suggests that although existing staff can handle the work, there is a need for additional support especially for weekend coverage and planning. | To improve the rating to Green, ensure that existing staffing levels are sufficient to cover all required periods including weekends. Consider conducting a resource assessment to identify staffing gaps and implement better support planning to handle short notice coverage needs effectively.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | partnership_and_collaboration | 2025-09-28 | Amber | The project status report shows that there is some level of existing collaboration between business and IT teams, as evidenced by statements like 'DBA team was able to provide weekend contacts to provide assistance if needed.' However, there are mentions of 'short notice given on needed support cause support planning issues' and 'misalignment on CR approval', indicating that additional team building is necessary to improve the relationship further. | To improve the rating to Green, it is essential to enhance collaboration by addressing identified misalignments and communication issues. Implementing structured team-building activities and improving communication protocols could help foster stronger relationships between business and IT teams, ensuring smoother project execution.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | solution​ | 2025-09-28 | Green | The project status report indicates that 'All project related task have been implemented,' and 'All remaining work clearly defined and assigned.' Moreover, while the project had been in red status previously, the report describes actions taken to correct this, stating, 'Project to be extended to Sept 30th, the extra time is to support the Shell team. this should correct the current RED status of the project and return it to green.' These details suggest that the solution is now understood and ready to mobilize. | Continue monitoring the project to ensure that any further issues are promptly addressed and that the solution remains ready to mobilize as planned. Maintain good communication with the Shell team and other stakeholders to ensure the project stays on track.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | ts_and_broader_rds_it_resource_Capacity | 2025-09-28 | Amber | There is a statement highlighting resource concerns: 'some concern on weekend coverage for migrations,' which suggests a request has been made but no firm commitments secured. | To achieve a Green rating, ensure formal commitments are obtained for necessary resources, especially concerning weekend coverage for migrations. Address any support planning issues to provide consistent and adequate coverage.
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | ts_process_team_within_comm_ops_bia_org​ | 2025-09-28 | Amber | There is evidence of concern regarding resources: 'some concern on weekend coverage for migrations.' This indicates that while current resources are generally sufficient, additional staffing or prioritization might still be necessary to meet certain requirements. | To achieve a Green rating, ensure that existing staff levels are truly sufficient by addressing the weekend coverage concern, potentially by reassessing staffing requirements during critical periods and adjusting priorities to optimize resource allocation effectively.