## Sheet1
Project Name | Number | Portfolio manager | Executive Summary | Planned end date | Planned start date | Updated | Phase | Comments | Comments on Budget | Comments on Cost | Comments on Resources | Comments on Schedule | Comments on Scope | Key Activities planned | Last Month's Achievements
DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | PRJ5030372 | David Gilmour (WYDGIU) | <p>Sept 2 - MDuke - No issues, Shell team had need for short term support, information was provided.</p> <p>Highlights - DBA team was able to provide weekend contacts to provide assistance if needed.</p> <p>Lowlights- short notice given on needed support cause support planning issues. </p> | 2025-10-13 17:00 | 2025-03-27 | 2025-09-02 20:11 | Executing | <p>Sept 2 - MDuke - no additional comments.</p> |  | <p>Sept 2 - MDuke - No issues.</p> | <p>Sept 2 - MDuke - some concern on weekend coverage for migrations.</p> | <p>sept 2 - MDuke - no issues.</p> | <p>Sept 2 - MDuke - no issues</p> | <p>Sept 2 - MDuke - only as needed support.</p> | <p>Sept 2 - Project deliverables were closed, Shell team requested additional support till the end of Sept to cover any issues.</p>
DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | PRJ5030372 | David Gilmour (WYDGIU) | <p>Aug 22 - MDuke - Project to be extended to Sept 30th, the extra time is to support the Shell team. this should correct the current RED status of the project and return it to green. </p> <p>Highlights: CR submitted, no issues.</p> <p>Lowlight: T-Sys Pm late in submitting CR, partially due to misalignment on CR approval.</p> <p> </p> <p>Aug 15 - MDuke - All project related task have been implemented, Customer requested more time to review before giving an approval to close.</p> <p>Highlights - All remaining work clearly defined and assigned.</p> <p>Lowlights - Project in red stauts, customer wanted more time to review the deliverables before giving project closure approval. </p> <p>Aug 5 - MDuke - CR requested to exten project end date and budget increase to cover additional work. The return to green plan is to extend the and date and budget, allow us to close the project on the 15th.</p> <p>Highlights - All remaining work clearly defined and assigned.</p> <p>Lowlights - Project in red stauts, customer wanted more time to review the deliverables before giving project closure approval. </p> | 2025-07-31 22:00 | 2025-03-27 | 2025-09-02 20:11 | Executing | <p>Aug 15 - MDuke - All project related task have been implemented, Customer requested more time to review before giving an approval to close.</p> <p>Au 5 - MDuke - The project is currently red dure to cost and schedule issues, these were raised due to operation concerns around the finding the changes made allows the Qlik application with the new account the ability to shut down the DB. change needed to be made to the HLD to describe this. And we wanted to make a document regarding the request process. </p> |  | <p>Aug 5 - MDuke - CR request sent to Shell, cost increase included.</p> |  | <p>Aug 15 - MDuke - Customer wanted more time to review the closure deliverables.</p> <p>Aug 5 - MDuke - requested end date extension to Aug 15th for final deliverables.</p> |  | <p>Aug 5 - M Duke - Complete request template, complete HLD, Handover to ops, Close the project.</p> | <p>Aug 5 - MDuke - RA completed. process for request defined.</p>
DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | PRJ5030372 | David Gilmour (WYDGIU) | <p>31 Jul - MDuke - Project is past end date status moved to red, RTG plan is to extend the project end Date to Aug 15 to complete the remaining task and to increase the budget to cover remaining work as well. Shell needs time to review and approve the budget and end date extension, but agrees the work need to be completed. Shell has a hard deadline to complete this project by Aug 31. </p> <p>Highlights - RA approved, cost and end date provided to Shell for approval.</p> <p>Lowlights - Project behind schedule and the status is now red.</p> <p>23 Jul - MDuke - After review with the project team there is still more effort needed to complete some components of the project namely Formalize Risk Acceptance, the Request Management Process, High-level design, and Handover to operations. The return to green plan is to extend the projects end date and increase the budget to accommodate the remaining work. </p> <p>Highlights - Work completed, Risk analysis and TTS to DB OPS in progress.</p> <p>Lowlights - Project budget exhausted. Additional time needed and budget needed to complete.</p> <p> </p> <p>18 Jul - MDuke - RA review still in progress.</p> <p>Highlights - Work completed, Risk analysis and TTS to DB OPS n progress.</p> <p>Lowlights - Project budget exhausted. </p> <p> </p> <p> </p> <p>8 Jul - MDuke - Glen Anderson working to help Shell complete RA to ensure that Shell understands the impacts of activating this service. All other project work is completed. </p> | 2025-07-31 17:00 | 2025-03-27 | 2025-09-02 20:11 | Executing | <p>8 - Jul - MDuke - no issues at this time.</p> |  | <p>Jul 25 - Project budget needs to be increase as the efforts to complete operationalize this project have required more effort than expected. the RTG is to work with customer to explain the needed funds and obtain them.</p> <p>8 - Jul - MDuke - Complete budget used </p> |  | <p>Jul 25 - Project end date extension needed to complete the following: Formalize Risk Acceptance, the Request Management Process, High-level design, and Handover to operations, end date change to Aug 29th will allow for the point to be properly discuss and implemented. </p> <p>Jul 9 - Dependent on forecast of storage growth or near-term need for capacity increase.</p> |  | <p>8 - Jul - MDuke - Closing project. </p> | <p>8 - Jul - MDuke - Project handed over from Niels. Discussions completed on RA requirements. </p>
DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | PRJ5030372 | David Gilmour (WYDGIU) | <p>Jun 18 - M Duke - PM Change complete, through the project is on target i would like clarity on some of the consequences of the actions taken so far to the security and performance of the DBs. </p> <p>Highlights - Work completed</p> <p>Lowlights - Need to Send risk acceptance to Shell, for close out</p> <p>June 5 Project is on schedule to be closed out end of this month</p> | 2025-07-03 17:00 | 2025-03-27 | 2025-09-02 20:11 | Executing | <p>planning close out end of June</p> |  | <p>Jun 18 - M Duke - On Target</p> | <p>Jun 18 - M Duke - no issues.</p> | <p>Jun 18 - M Duke - Project progressing, need clarity from ops and IRM for close out.</p> | <p>Jun 18 - M Duke - No issues at this time.</p> | <p>June 18</p> <p>Close out end of June</p> | <p>May-</p> <p>verified solution direction</p>