## Sheet1
project_id | project_name | optic_name | rating_date | rating | justification | recommendation
PRJ5030372 | DMND0030713_T1PRJ0006688_Qlik Replicate ASM Credential Handling_TSI | firmness_of_opportunity | 2025-09-28 | Red | The report does not provide any evidence of DAF / GIP or 'one pager' prepared, nor indications of all internal approvals obtained. The start date of the IT effort is known as March 27, 2025, but there are no specifics on approvals or their expected timeline. History of schedule changes and issues imply that approvals might not be forthcoming soon. | To move towards a Green rating, ensure that DAF / GIP or 'one pager' is prepared and obtain all necessary internal approvals from impacted portfolios. Establish a clear and committed timeline for obtaining these approvals to prevent further delays.